## Slide 1
CMMI Overview Training
Capability Maturity Model - Integrated for Development
Hari Prasad Thapliyal
PMP, PMI-ACP, CSM, MBA, MCA, PGDOM, PGDFM, CIC, PRINCE2-Practitioner
PMO Architect & Project Management Evangelist
Vedavit Project Solutions
Cell: +91-95-3599-9336
Email: hari.Prasad@vedavit-ps.com
Website: www.pmlogy.com
@ Capability Maturity Model, Capability Maturity Modeling, CMM and CMMI are registered in the US Patent and Trademark Office. Copyright 2012 by Carnegie Mellon University

## Slide 2: Introduction
Name
Position
Background
Experience in process improvement activities

## Slide 3
Day 1
Introduction to CMMi
Generic processes in CMMi
Process Management processes
Day 2
Project Management processes
Engineering Processes
Day 3
Support processes
Summary and Discussions

## Slide 4: Module 1 - Introduction to CMMI

## Slide 5: Technical Details
Current Version –1.3
Representation : Staged and Continuous
Available models (CMM I SE/SW, CMM I SW, CMM I SE/SW/IPPD, CMM I SE/SW/SS/IPPD, CMM I SE/SW/SS)
Assessment method : ARC / SCAMPI Ver 1.1

## Slide 6: CMMI Source Models
The CMM Integration Project was formed to
  build an initial set of integrated models
  establish a framework to enable integration of future models
  create an associated set of appraisal and training products
Source Models serving as inputs for the team were
  Capability Maturity Model for Software V2, draft C (SW-CMM V2C)
  EIA Interim Standard 731, System Engineering Capability Model (SECM)
  Integrated Product Development Capability Maturity Model, draft v0.98 (IPD-CMM)

## Slide 7: The CMMI Solution: A product Line Approach
SW
Assess
SE
IPPD
Training
Industry
SEI
Government
CMMI
Product
Suite
Team of Teams
Modeling & Discipline Experts
Collaborative Process
CMMI -
SE/SW
CMMI -
SE/SW/
IPPD/SS
CMMI -
SW
CMMI -
SE/SW/
IPPD

## Slide 8: CMMI Model Representations
An organization may choose to approach process improvement from either the
  Process capability approach
  Organizational Maturity approach
CMMI model supports each approach with a representation
  Process Capability approach – continuous representation
  Organizational Maturity approach – staged representation

## Slide 9: Staged Representation
Provides a proven sequence of improvements, each serving as a foundation for the next
Permits comparisons across and among organizations by the use of maturity levels
Provides an easy migration from the SW-CMM to CMMI
Provides a single rating that summarizes appraisal results and allows comparisons among organizations

## Slide 10: Continuous Representation
Allows you to select the order of improvement that best meets your organization’s business objectives and mitigates your organization’s areas of risk
Enables comparisons across and among organizations on a process area by process area basis
Provides an easy migration from EIA/IS-731 to CMMI

## Slide 11: CMMI Model Terminology
Item | Staged | Continuous
 | Maturity Levels | Capability Levels Equivalent Staging
Rating Component | Process Areas Process Area Goals | Process Areas Process Area Goals
Implementing Practices | Specific Practices | Specific Practices Advanced Practices
Institutionalizing Practices | Common Features Commitment Ability Directing Implementation Verifying Implementation | Generic Practices

## Slide 12: Structure of the CMMI Staged Representation
Maturity Levels
Process Area 2
Process Area 1
Process Area n
Specific
Goals
Generic
Goals
Specific
Practices
Ability to Perform
Commitment to Perform
Verifying Implementation
Directing Implementation
Common Features
Generic Practices

## Slide 13: The Maturity Levels
Initial
Defined
Managed
Quantitatively
Managed
Optimizing
5
4
3
2
1
Process unpredictable,
poorly controlled, and
reactive
Process characterized for projects
and is often reactive
Focus on process improvement
Process measured and controlled
Process characterized for the organization
and is proactive

## Slide 14: The Process Areas
Requirements Management
Project Planning
Project Monitoring and Control
Supplier Agreement Management
Measurement and Analysis
Process and Product Quality Assurance
Configuration Management
Organizational Innovation and Deployment
Causal Analysis and Resolution
Organizational Process Performance
Quantitative Project Management
Requirements Development
Technical Solution
Product Integration
Verification
Validation
Organizational Process Focus
Organizational Process Definition
Organizational Training Integrated Project Management for IPPD
Risk Management
Integrated Teaming
Integrated Supplier Management
Decision Analysis and Resolution
Organizational Environment for Integration
2 Managed
1 Initial
No Process Areas
3 Defined
4 Quantitatively
Managed
5 Optimizing
Basic Project Management
Standard, consistent process achieving process standardization
Continuously improving process
Predictable process and Quantitative Management

## Slide 15: Structure of the CMMI Continuous Representation
Process Area 2
Process Area 1
Process Area n
Specific
Goals
Generic
Goals
Specific
Practices
Generic
Practices
Capability Levels

## Slide 16: Process Capability Levels
Performed
Defined
Managed
Quantitatively Managed
5
4
3
2
1
Optimizing
Incomplete
0

## Slide 17: Continuous Representation
In the continuous representation, there are four defined categories of CMMI process areas
Process Management Processes
Project Management Processes
Engineering Processes
Support Processes

## Slide 18: Process Area Categories
Project
Management
Process Areas
Category
Requirements Management
Requirements Development
Technical Solution
Product Integration
Verification
Validation
Engineering
Configuration Management
Process and Product Quality Assurance
Measurement and Analysis
Decision Analysis and Resolution
Organizational Environment for Integration Causal Analysis and Resolution
Support
Project Planning
Project Monitoring and Control
Supplier Agreement Management
Integrated Project Management for IPPD
Risk Management Integrated Teaming
Integrated Supplier Management
Quantitative Project Management
Organizational Process Focus
Organizational Process Definition
Organizational Training
Organizational Process Performance
Organizational Innovation and Deployment
Process
Management

## Slide 19: IPPD Definition
The CMMI-SE/SW/IPPD defines IPPD as follows:
IPPD is a systematic approach to product development that achieves a timely collaboration of relevant stakeholders throughout the product life cycle to better satisfy customer needs

## Slide 20: IPPD Background
IPPD expands on concurrent engineering by adding processes e.g.,
Product related processes are developed or tailored from standard processes concurrently with the product development
Teams involve relevant stakeholders spanning the lifecycle of the product
IPPD also expand on the technical integration employed in a disciplined, systems engineering approach, to integrate business functions as well as technical functions.

## Slide 21: IPPD Process Areas
Organization Environment for Integration – focuses at the organizational aspects
Integrated Project Management (Level 3) – 2 Specific Goals – focuses at the project aspects
Integrated Teaming – focuses at the team aspects

## Slide 22: Model Components - 1
Specific Goals: A specific goal applies to a process area and addresses the unique characteristics that describe what must be implemented to satisfy the process area.
Specific Practice: A specific practice is an activity that is considered important in achieving the associated specific goal.

## Slide 23: Model Components - 2
Two types of Specific Practices in the continuous representation
  Base Practices
  Advanced Practices: Certain advanced practices show an evolution from a base practice to a higher capability level.

## Slide 24: Model Components - 3
Generic Goals: Common goal statement for a process area and the target is for achieving institutionalization.
  Achievement of a generic goal in a process area signifies improved control in planning and implementing the processes associated with that process area.
  Generic goals are called “generic” because the same goal statement appears in multiple process areas.
  Each capability level has an associated generic goal.
  Covered in detail in next module

## Slide 25: Model Components - 4
Generic Practices: Generic practices are activities that ensure that the processes associated with the process area will be effective, repeatable, and lasting. (targeting institutionalization)
Generic practices contribute to the achievement of the generic goal when applied to a particular process area
Covered in detail in next module

## Slide 26: Model Components - 5
Required Components:
  Specific goals and generic goals are required.
These model components
  are essential to achieving process improvement in a given process area
  are used in appraisals to determine process area capability

## Slide 27: Model Components - 6
Expected Components:
  Specific practices and generic practices are expected.
These model components
  explain what will typically be done to cover the scope of the process and its goals
  are meant to guide model users and help appraisers
  allow acceptable alternatives

## Slide 28: Model Components - 7
Informative
  Everything else is informative.
  Notes, typical work products, sub-practices, discipline amplifications, and generic practice elaborations are informative.
These model components provide details about the model.

## Slide 29: Module 2 - Generic Goals and Practices
@ Capability Maturity Model, Capability Maturity Modeling, CMM and CMMI are registered in the US Patent and Trademark Office. Copyright 2000 by Carnegie Mellon University

## Slide 30: Prelude
Objective is to give an insight in to Generic processes
Caution : Slides are Verbose and no graphics used through out the presentation
Focus is on discussion

## Slide 31: Generic Goals (GG)
GG 2 – Institutionalize a Managed Process (Level 2)
GG 3 – Institutionalize a Defined Process (Level 3, Level 4 and Level 5)

## Slide 32: Generic Goals (GG)
Commitment to Perform
Ability to Perform
Directing Implementation
Verifying implementation

## Slide 33: Managed Process
A “managed process” is a performed process that is planned and executed in accordance with policy; employs skilled people having adequate resources to produce controlled outputs; involves relevant stakeholders; is monitored, controlled, and reviewed; and is evaluated for adherence to its process description.

## Slide 34: Defined Process
A “defined process” is a managed process that is tailored from the organization’s set of standard processes according to the organization’s tailoring guidelines; has a maintained process description; and contributes work products, measures, and other process-improvement information to the organizational process assets.

## Slide 35: GG2 Institutionalize a Managed Process
GG 2 | Institutionalize a Managed Process
GP 2.1 GP 2.2 GP 2.3 GP 2.4 GP 2.5 GP 2.6 GP 2.7 GP 2.8 GP 2.9 GP 2.10 | Establish an Organizational Policy Plan the Process Provide Resources Assign Responsibility Train People Manage Configurations Identify and Involve Relevant Stakeholders Monitor and Control the Process Objectively Evaluate Adherence Review Status with Higher Level Management

## Slide 36: GG3 Institutionalize a Defined Process
GG 3 | Institutionalize a Defined Process
GP 3.1 GP 3.2 | Establish a Defined Process Collect Improvement Information

## Slide 37: Commitment to Perform
Purpose
The Commitment to perform (CO) groups the generic practices related to creating policies and securing sponsorship

## Slide 38: GP 2.1 Establish an organizational policy
Define the organizational expectations for the process
Document and make the expectations visible to all
Organizational direction with the sponsorship from Senior Management

## Slide 39: Ability to Perform
Purpose
Ability to perform (AB) groups the generic practices related to ensuring that the project and/or organization has the resources it needs

## Slide 40: GP 2.2 Plan the process
For every process area:
Determine what is needed to perform the process area and achieve established objectives
Prepare a plan for performing the process and review with stakeholders
Process description for the process
Specify performance objectives like quality, time scale, cycle time and resource usage

## Slide 41: GP 2.3 Provide resources
For every process area:
Resources that are defined in the plan are provided
Resources include adequate funding, physical facilities, skilled people and tools

## Slide 42: GP 2.4 Assign Responsibility
For every process area:
Accountability is assigned for performing the process and specific tasks in the process, and achieving the specified results
Responsibilities and authorities defined using detailed job descriptions or other means
Confirm that the people assigned to the responsibilities and authorities understand and accept them

## Slide 43: GP 2.5 Train People
For every process area:
Ensure people have the necessary skills and expertise to perform or support the process
Appropriate training is provided to people who will be performing work
Overview training is provided to orient people who interact with those performing work

## Slide 44: GP 3.1 Establish a defined process
For every process area:
Select from the organization's set of standard processes those processes that cover the process area and best meet the needs of the project or organizational function.
Establish the defined process by tailoring the selected processes according to the organization's tailoring guidelines.
Ensure that the organization's process objectives are appropriately addressed in the defined process.
Document the defined process and the records of the tailoring.
Revise the description of the defined process as necessary.

## Slide 45: Directing implementation
Purpose
Directing implementation (DI) groups the generic practices related to managing the performance of the process, managing the integrity of its work products, and involving relevant stakeholders

## Slide 46: GP 2.6 Managing Configurations
For every process area:
Definition of work products placed under configuration
Method / Type of configuration control

## Slide 47: GP 2.7 Identify and involve relevant stakeholders
For every process area:
Identify and involve relevant stakeholders in the activities such as planning, decisions, communications, coordination, reviews, appraisals, resolution of problems
Ensure that interactions necessary are planned, documented and accomplished

## Slide 48: GP 2.8 Monitor and control the process
For every process area:
To perform day to day monitoring and controlling the process
Measure appropriate attributes of the process or work products produced by the process
Identify and evaluate effects of significant deviation from the plan for performing the process
Take corrective action as required and track it to closure

## Slide 49: GP 3.2 Collect Improvement Information
For every process area:
Applicable for Level 3 and above
Objective is to improve the organizations processes and process assets by :
  Collecting work products, measures, measurement results and improvement suggestions

## Slide 50: Verifying implementation
Purpose
Verifying implementation (VE) groups the generic practices related to review by higher level management and objective evaluation of conformance to process descriptions, procedures and standards

## Slide 51: GP 2.9 Objectively evaluate adherence
For every process area:
Provide credible assurance that the process is implemented as planned and adheres to its process description, standards and procedures
People not directly responsible for managing or performing evaluate adherence
Track the issues to closure

## Slide 52: GP 2.10 Review Status with Higher Level Management
For every process area:
Provide higher level management with the visibility into the process
Reviews are both periodic and event driven
Objective is for the Senior Management to ensure policies and objectives are followed and achieved

## Slide 53: Generic Practices at Level 2
Senior Management Directives
Policy
Training Needs
Plans
Plans, Estimates,
Process Descriptions
Resources
Responsibility
Training Needs
Identification of CI
Identification of Stakeholders
Revisions to Responsibilities
Manage CI
Manage stakeholders
Monitor Plan and Process
Monitor (Status Reports,
MOMs, Tracking sheets, etc)
Evaluate: Audit of processes and Work Products
Review with Senior Management
How does this change for GG 3 ?

## Slide 54: Generic Practices at Level 3
Senior Management Directives
Policy
Training Needs
Revisions to Responsibilities
Manage CI
Manage stakeholders
Monitor Plan and Process
Monitor (Status Reports,
MOMs, Tracking sheets, etc)
Review with Senior Management
Plans
Plans, Estimates, Resources
Responsibility, Training Needs
Identification of CI,
Identification of Stakeholders
Organizational Set of Standard Processes
With tailoring guidelines & criteria
Contribute to Organizational Repository
(Measures, Improvement Information, Artifacts)
Defined Process
at Project Level
Evaluate: Audit of processes and Work Products

## Slide 55: Module 3 - Process Management Process Areas

## Slide 56: Prelude
Objective is to give an overview of Process Management processes
Caution : Slides are Verbose and no animation used through out the presentation
Focus is on discussion

## Slide 57: Scope
Basic Process Management Processes
Organizational Process Focus (L3)
Organizational Process Definition (L3)
Organizational Training (L3)
Advanced Process Management Processes
Organizational Process Performance (L4)
Organizational Innovation and Deployment (L5)

## Slide 58: Organizational Process Focus
Purpose
The purpose of Organizational Process Focus is to plan and implement organizational process improvement based on a thorough understanding of the current strengths and weaknesses of the organization’s processes and process assets

## Slide 59: Organizational Process Focus
SG 1 | Determine Process Improvement Opportunities
SP 1.1 SP 1.2 SP 1.3 | Establish Organizational Process Needs Appraise the Organization’s processes Identify the Organization’s Process Improvements
SG 2 | Plan and Implement Process Improvement Activities
SP 2.1 SP 2.2 SP 2.3 SP 2.4 | Establish Process Action Plans Implement Process Action Plans Deploy organizational Process Assets Incorporate process related experiences into the Organization’s Process Assets

## Slide 60: Important Points / New Aspects..
Identify the policies, standards and business objectives
Determine organization’s process performance objectives (e.g. cycle time, productivity)
Periodic process appraisals based on standards
Ensure that results of implementing process action plans satisfy the organization’s process improvement objectives
Conduct periodic reviews of the effectiveness and suitability of processes
Analyze organizations common set of measures

## Slide 61: Work Products
Discussions on probable work products

## Slide 62: Organizational Process Definition
Purpose
The purpose of Organizational Process Definition is to establish and maintain a usable set of organizational process assets

## Slide 63: Organizational Process Definition
SG 1 | Create Organizational Process Assets
SP 1.1 SP 1.2 SP 1.3 SP 1.4 SP 1.5 | Establish Standard Processes Establish Life-Cycle Model Descriptions Establish Tailoring Criteria and Guidelines Establish the Organization’s Measurement Repository Establish the Organization’s Process Asset Library

## Slide 64: Important Points / New Aspects..
Decompose each standard process into process elements
Specify critical attributes of each process element
Specify the relationships of the process elements (e.g. ordering, interfaces, interdependencies)
Procedure for storing, retrieving, cataloging, issue for use by projects, periodically reviewing the usefulness of contents and revising the asset library

## Slide 65: Work products
A discussion

## Slide 66: Organizational Training
Purpose
The purpose of Organizational Training is to develop the skills and knowledge of people so they can perform their roles effectively and efficiently

## Slide 67: Organizational Training
SG 1 | Establish an Organizational Training capability
SP 1.1 SP 1.2 SP 1.3 SP 1.4 | Establish strategic training needs Determine which training needs are the responsibility of the organization Establish an organizational training tactical plan Establish Training Capability
SG 2 | Provide Necessary Training
SP 2.1 SP 2.2 SP 2.3 | Deliver Training Establish Training Records Assess Training effectiveness

## Slide 68: Important Points / New Aspects..
Analyze Strategic Business objectives and process improvement plans
Take decisions to develop or acquire training
Develop Organizations training curriculum
Provide a mechanism for assessing effectiveness of each training course against established objectives

## Slide 69: Discussion
Challenges in selecting training approaches
Work products

## Slide 70: Organizational Process Performance
Purpose
The purpose of Organizational Process Performance is to establish and maintain a quantitative understanding of the performance of the organization’s set of standard processes in support of quality and process-performance objectives, and to provide process performance data, baselines, and models to quantitatively manage the organization’s projects

## Slide 71: Organizational Process Performance
SG 1 | Establish Performance Baselines and Models
SP 1.1 SP 1.2 SP 1.3 SP 1.4 SP 1.5 | Select Processes Establish Process performance measures Establish Quality and Process-performance objectives Establish Process performance baselines Establish Process performance models

## Slide 72: Important Points / New Aspects..
Select processes based on the needs and objectives of organization and projects
Establishing a common set of process performance measures based on quantitative objectives for quality and performance
Establish and maintain the organization’s process performance baselines
Establish and maintain Process performance models and its usage at various levels
Calibrate process performance models

## Slide 73: Discussion
How much data is required for arriving at Process performance baselines ?
How do we promote usage of performance baselines and models ?
Probable Work Products

## Slide 74: Organizational Innovation and Deployment
Purpose
The purpose of Organizational Innovation and Deployment is to select and deploy incremental and innovative improvements that measurably improve the organization’s processes and technologies. The improvements support the organization’s quality and process performance objectives as derived from the organization’s business objectives

## Slide 75: Organizational Innovation and Deployment
SG 1 | Select improvements
SP 1.1 SP 1.2 SP 1.3 SP 1.4 | Collect and analyze improvement proposals Identify and analyze innovations Pilot improvements Select improvements for deployment
SG 2 | Deploy Improvements
SP 2.1 SP 2.2 SP 2.3 | Plan the deployment Manage the deployment Measure improvement effects

## Slide 76: Important Points / New Aspects..
Collect Process and Technology improvement proposals
Identify innovative proposals
Identify potential barriers and risks of deployment
Investigate innovative improvements that may improve OSSP
Establish measures and objectives for determining value of each process
Determine deployed improvements meet quality and process performance parameters set

## Slide 77: Discussion
How do we differentiate improvements and innovations ?
Probable work products

## Slide 78: Module 4 - Project Management Process Areas

## Slide 79: Prelude
Objective is to give an overview of Project Management processes
Caution : Slides are Verbose and no animation used through out the presentation
Focus is on discussion

## Slide 80: Scope
Basic Project Management Processes
  Project Planning (L2)
  Project Monitoring and Control (L2)
  Supplier Agreement Management (L2)
Advanced Project Management Processes
  Integrated Project Management for IPPD (or Integrated Project Management) (L3) (IPPD covered separately – Module 7)
  Risk Management (L3)
  Integrated Teaming L3) - (IPPD covered separately – Module 7)
  Integrated Supplier Management (L3)
  Quantitative Project Management (L4)

## Slide 81: Project Planning
The purpose of Project Planning is to establish and maintain plans that define project activities

## Slide 82: Project Planning
SG 1 | Establish Estimates
SP 1.1 SP 1.2 SP 1.3 SP 1.4 | Estimate the Scope of the Project Establish Estimates of Work Product and Task Attributes Define Project Life Cycle Determine Estimates of Effort and Cost

## Slide 83: Project Planning
SG 2 | Develop a Project Plan
SP 2.1 SP 2.2 SP 2.3 SP 2.4 SP 2.5 SP 2.6 SP 2.7 | Establish the Budget and Schedule Identify Project Risks Plan for Data Management Plan for Project Resources Plan for Needed Knowledge and Skills Plan Stakeholder Involvement Establish the Project Plan

## Slide 84: Project Planning
SG 3 | Obtain Commitment to the Plan
SP 3.1 SP 3.2 SP 3.3 | Review Plans that Affect the Project Reconcile Work and Resource Levels Obtain Plan Commitment

## Slide 85: Important Points / New Aspects..
Develop a WBS based on the product architecture
Identify the work packages in sufficient detail to specify estimates of project tasks, responsibilities, and schedule
Identify work products (or components of work products) that will be externally acquired
Identify work products that will be reused
Use appropriate methods to determine the attributes of the work products and tasks that will be used to estimate the resource requirements
Review and obtain agreement with relevant stakeholders on the completeness and correctness of the documented risks

## Slide 86: Important Points / New Aspects..
Establish requirements and procedures to ensure privacy and security of the data
Determine facilities, equipment, and component requirements
Reconcile Work and Resource Levels
Identify commitments on interfaces between elements in the project, and with other projects and organizational units, so they can be monitored

## Slide 87: Discussion
Probable work products
Influence of type of projects on estimation models
Impact of Service Level Agreements on commitments

## Slide 88: Project Monitoring and Control
The purpose of Project Monitoring and Control is to provide an understanding of the project’s progress so that appropriate corrective actions can be taken when the project’s performance deviates significantly from the plan

## Slide 89: Project Monitoring and Control
SG 1 | Monitor project against plan
SP 1.1 SP 1.2 SP 1.3 SP 1.4 SP 1.5 SP 1.6 SP 1.7 | Monitor Project Planning Parameters Monitor Commitments Monitor Project Risks Monitor Data Management Monitor Stakeholder Involvement Conduct Progress Reviews Conduct Milestone Reviews

## Slide 90: Project Monitoring and Control
SG 2 | Manage Corrective Action to Closure
SP 2.1 SP 2.2 SP 2.3 | Analyze Issues Take Corrective Action Manage Corrective Action

## Slide 91: Important Points / New Aspects..
Monitor the attributes of the work products and tasks
Monitor the knowledge and skills of project personnel
Document the results of the commitment reviews
Revise the documentation of the risks, as additional information becomes available, to incorporate changes
Communicate risk status to relevant stakeholders
Periodically review data management activities against their description in the project plan
Document the results of the stakeholder involvement status reviews

## Slide 92: Discussions
Probable work products

## Slide 93: Supplier Agreement Management
The purpose of Supplier Agreement Management is to manage the acquisition of products from suppliers for which there exists a formal agreement
This process area will be looked at in more detail to understand differences with Subcontract Management KPA in CMM

## Slide 94: Supplier Agreement Management
SG 1 | Establish Supplier Agreements
SP 1.1 SP 1.2 SP 1.3 | Determine Acquisition Type Select Suppliers Establish Supplier Agreements
SG 2 | Satisfy Supplier Agreements
SP 2.1 SP 2.2 SP 2.3 SP 2.4 | Review COTS Products Execute the Supplier Agreement Accept the Acquired Product Transition Products

## Slide 95: SP 1.1 Determine Acquisition Type
No sub practices

## Slide 96: SP 1.2 Select Suppliers
Establish and document criteria for evaluating potential suppliers
Identify potential suppliers and distribute solicitation material and requirements to them
Evaluate proposals according to evaluation criteria
Evaluate risks associated with each proposed supplier
Evaluate proposed suppliers' ability to perform the work
Select the supplier

## Slide 97: SP 1.3 Establish Supplier Agreements
Revise the requirements to be fulfilled by the supplier to reflect negotiations with the supplier when necessary
Document what the project will provide to the supplier
Document the supplier agreement
Ensure all parties to the agreement understand and agree to all requirements before implementing
Revise the supplier agreement as necessary
Revise the project’s plans and commitments as necessary to reflect the supplier agreement

## Slide 98: SP 2.1 Review COTS Products
Develop criteria for evaluating COTS products
Evaluate candidate COTS products against the associated requirements and criteria
Evaluate the impact of candidate COTS products on the project's plans and commitments
Assess the suppliers' performance and ability to deliver
Identify risks associated with the selected COTS product and the supplier agreement
Select the COTS product to be acquired
Plan for the maintenance of the COTS product

## Slide 99: SP 2.2 Execute the Supplier Agreement
Monitor supplier progress and performance (schedule, effort, cost, and technical performance) as defined in the supplier agreement
Monitor selected supplier processes and take corrective action when necessary
Conduct reviews with the supplier as specified in the supplier agreement
Conduct technical reviews with the supplier as defined in the supplier agreement
Conduct management reviews with the supplier as defined in the supplier agreement

## Slide 100: SP 2.2 Execute the Supplier Agreement
Use the results of reviews to improve the supplier's performance and to establish and nurture long-term relationships with preferred suppliers
Monitor risks involving the supplier and take corrective action as necessary
Revise the supplier agreement and project plans and schedules as necessary

## Slide 101: SP 2.3 Accept the Acquired Product
Define the acceptance procedures
Review and obtain agreement with relevant stakeholders on the acceptance procedures before the acceptance review or test
Verify that the acquired products satisfy their requirements
Confirm that the non technical commitments associated with the acquired work product are satisfied

## Slide 102: SP 2.3 Accept the Acquired Product
Document the results of the acceptance review or test
Establish and obtain supplier agreement on an action plan for any acquired work products that do not pass their acceptance review or test
Identify, document, and track action items to closure

## Slide 103: SP 2.4 Transition Products
Ensure that there are appropriate facilities to receive, store, use, and maintain the acquired products
Ensure that appropriate training is provided for those involved in receiving, storing, using, and maintaining the acquired products
Ensure that storing, distributing, and using the acquired products are performed according to the terms and conditions specified in the supplier agreement or license

## Slide 104: Integrated Project Management for IPPD
The purpose of Integrated Project Management is to establish and manage the project and the involvement of the relevant stakeholders according to an integrated and defined process that is tailored from the organization's set of standard processes
For Integrated Product and Process Development, Integrated Project Management also covers the establishment of a shared vision for the project and a team structure for integrated teams that will carry out the objectives of the project – Covered in Module 7.

## Slide 105: Integrated Project Management
SG 1 | Use the Project’s Defined Process
SP 1.1 SP 1.2 SP 1.3 SP 1.4 SP 1.5 | Establish the Project’s Defined Process Use Organizational Process Assets for Planning Project Activities Integrate Plans Manage the Project Using the Integrated Plans Contribute to the Organizational Process Assets

## Slide 106: Integrated Project Management
SG 2 | Coordinate and Collaborate with Relevant Stakeholders
SP 2.1 SP 2.2 SP 2.3 | Manage Stakeholder Involvement Manage Dependencies Resolve Coordination Issues

## Slide 107: Important Points / New Aspects..
Integrate other plans that affect the project with the project plan
Identify and analyze product and project interface risks
Establish objective entry and exit criteria to authorize the initiation and completion of the tasks described in the work breakdown structure (WBS)
Identify how conflicts will be resolved that arise among relevant stakeholders
Propose improvements to the organizational process assets
Submit documentation for possible inclusion in the organization's process asset library

## Slide 108: Important Points / New Aspects..
Document lessons learned from the project for inclusion in the organization's process asset library
Review and get agreement on the commitments to address each critical dependency with the people responsible
Track the critical dependencies and commitments and take corrective action as appropriate

## Slide 109: Risk Management
The purpose of Risk Management is to identify potential problems before they occur, so that risk-handling activities may be planned and invoked as needed across the life of the product or project to mitigate adverse impacts on achieving objectives

## Slide 110: Risk Management
SG 1 | Prepare for Risk Management
SP 1.1 SP 1.2 SP 1.3 | Determine Risk Sources and Categories Define Risk Parameters Establish a Risk Management Strategy
SG 2 | Identify and Analyze Risks
SP 2.1 SP 2.2 | Identify Risks Evaluate, Categorize, and Prioritize Risks

## Slide 111: Risk Management
SG 3 | Mitigate Risks
SP 3.1 SP 3.2 | Develop Risk Mitigation Plans Implement Risk Mitigation Plans

## Slide 112: Important Points / New Aspects..
Detailed analysis on risk sources and categories
Define bounds on the extent to which thresholds are applied against or within a category
Review all elements of the work breakdown structure and project plan as part of identifying risks to help ensure that all aspects of the work effort have been considered
Identify the person or group responsible for addressing each risk
Determine the cost-to-benefit ratio of implementing the risk mitigation plan for each risk
Develop contingency plans for selected critical risks in the event their impacts are realized
Collect performance measures on the risk-handling activities

## Slide 113: Discussion
Constraints in Risk Management
Probable work products

## Slide 114: Integrated Supplier Management
The purpose of Integrated Supplier Management is to proactively identify sources of products that may be used to satisfy the project’s requirements and to manage selected suppliers while maintaining a cooperative project-supplier relationship

## Slide 115: Integrated Supplier Management
SG 1 | Analyze and Select Sources of Products
SP 1.1 SP 1.2 | Analyze Potential Sources of Products Evaluate and Determine Sources of Products
SG 2 | Coordinate Work with Suppliers
SP 2.1 SP 2.2 SP 2.3 | Monitor Selected Supplier Processes Evaluate Selected Supplier Work Products Revise the Supplier Agreement or Relationship

## Slide 116: SP 1.1 Analyze Potential Sources of Products
Conduct market research to identify potential sources of candidate products to be acquired, including candidates from suppliers of custom-made products and vendors of COTS products
Evaluate potential sources against established criteria by performing trade studies, as appropriate
Identify risks associated with the potential sources

## Slide 117: SP 1.2 Evaluate and Determine Sources of Products
Determine the feasibility of acquiring custom-made or off-the-shelf products
Determine product life-cycle costs of custom-made or off-the-shelf products
Use the results of these analyses to select a supplier

## Slide 118: SP 2.1 Monitor Selected Supplier Processes
Identify the supplier processes that are critical to the success of the project
Monitor the selected supplier’s processes for compliance with requirements of the agreement
Analyze the results of monitoring the selected processes to detect issues as early as possible that may affect the supplier’s ability to satisfy the requirements of the agreement

## Slide 119: SP 2.2 Evaluate Selected Supplier Work Products
Identify those work products that are critical to the success of the project and that should be evaluated to help detect issues as early as possible that may affect the supplier’s ability to satisfy the requirements of the agreement
Evaluate the selected work products
Determine and document actions needed to address deficiencies identified in the evaluations

## Slide 120: SP 2.3 Revise the Supplier Agreement or Relationship
Review the supplier agreement to ensure it accurately reflects the project’s relationship with the supplier and current market conditions
Revise the project’s defined process or work products as necessary to reflect changes in the project-supplier relationship
Ensure that the supplier’s processes or work products are revised as necessary to reflect changes in the project-supplier relationship

## Slide 121: SP 2.3 Revise the Supplier Agreement or Relationship
Coordinate changes to the supplier agreement with the supplier to ensure that changes in the project-supplier relationship are understood by both the project and supplier
Adapt the supplier agreement or relationship to better match the supplier’s performance based on the results of risk evaluations
Communicate to project members and other relevant stakeholders all changes to the supplier agreement and to the project-supplier relationship

## Slide 122: Quantitative Project Management
The purpose of the Quantitative Project Management process area is to quantitatively manage the project’s defined process to achieve the project’s established quality and process-performance objectives

## Slide 123: Quantitative Project Management
SG 1 | Quantitatively Manage the Project
SP 1.1 SP 1.2 SP 1.3 SP 1.4 | Establish the Project’s Objectives Compose the Defined Process Select the Sub processes that Will Be Statistically Managed Manage Project Performance

## Slide 124: Quantitative Project Management
SG 2 | Statistically manage sub process performance
SP 2.1 SP 2.2 SP 2.3 SP 2.4 | Select Measures and Analytic Techniques Apply Statistical Methods to Understand Variation Monitor Performance of the Selected Sub processes Record Statistical Management Data

## Slide 125: Important Points / New Aspects..
Review the organization's objectives for quality and process performance
Derive interim objectives for each life-cycle phase, to monitor progress in achieving the project’s objectives
Establish traceability to the project’s quality and process-performance objectives from their sources
Determine whether the sub processes that are to be statistically managed, are suitable for statistical management
Analyze the interaction of sub processes to understand the relationships among the sub processes and the measured attributes of the sub processes
Select the sub processes that will be statistically managed using the selection criteria

## Slide 126: Important Points / New Aspects..
Periodically review the performance of each sub process and the capability of each sub process selected to be statistically managed, to appraise progress toward achieving the project’s quality and process-performance objectives
Use process performance models calibrated with obtained measures of critical attributes to estimate progress toward achieving the project’s quality and process-performance objectives
Specify the operational definitions of the measures, their collection points in the sub processes, and how the integrity of the measures will be determined
Identify the appropriate statistical analysis techniques that are expected to be useful in statistically managing the selected sub processes

## Slide 127: Important Points / New Aspects..
Calculate the natural bounds of process performance for each measured attribute
Identify and document sub process capability deficiencies
Determine and document actions needed to address sub process capability deficiencies

## Slide 128: Discussion
Selection of appropriate sub process goals
Probable work products

## Slide 129: Module 5 - Engineering Process Areas

## Slide 130: Prelude
Objective is to give an overview of Engineering processes
Moderate knowledge level of CMM assumed
Novices may have to participate more
Caution : Slides are Verbose and no animation used through out the presentation
Focus is on discussion

## Slide 131: Scope
Engineering Processes
Requirements Development (L3)
Requirements Management (L2)
Technical Solution (L3)
Product Integration (L3)
Verification (L3)
Validation (L3)

## Slide 132: Requirements Management
The purpose of Requirements Management is to manage the requirements of the project's products and product components and to identify inconsistencies between those requirements and the project's plans and work products

## Slide 133: Requirements Management
SG 1 | Manage Requirements
SP 1.1 SP 1.2 SP 1.3 SP 1.4 SP 1.5 | Obtain an Understanding of Requirements Obtain Commitment to Requirements Manage Requirements Changes Maintain Bi-directional Traceability of Requirements Identify Inconsistencies between Project Work and Requirements

## Slide 134: Important Points / New Aspects..
Requirements allocation handled in Requirements development
Objective criteria for the acceptance of requirements
Impact on the project participants should be evaluated when the requirements change or at the start of a new requirement
Maintain requirements traceability from a requirement to its derived requirements as well as to its allocation of functions, objects, people, processes, and work products
Maintain horizontal traceability from function to function and across interfaces
Review the project's plans, activities, and work products for consistency with the requirements and the changes made to them

## Slide 135: Expected work products
Discussion

## Slide 136: Requirements Development
The purpose of Requirements Development is to produce and analyze customer, product, and product-component requirements

## Slide 137: Requirements Development
SG1 | Develop Customer Requirements
SP 1.1 SP 1.2 | Elicit Needs Develop the Customer Requirements
SG 2 | Develop Product Requirements
SP 2.1 SP 2.2 SP 2.3 | Establish Product and Product-Component Requirements Allocate Product-Component Requirements Identify Interface Requirements

## Slide 138: Requirements Development
SG 3 | Analyze and Validate Requirements
SP 3.1 SP 3.2 SP 3.3 SP 3.4 SP 3.5 | Establish Operational Concepts and Scenarios Establish a Definition of Required Functionality Analyze Requirements Analyze Requirements to Achieve Balance Validate Requirements with Comprehensive Methods

## Slide 139: Important Points / New Aspects..
Engaging relevant stakeholders using methods for eliciting needs, expectations, constraints and external interfaces
Define constraints for verification and validation
Develop and review operational concepts and scenarios that include functionality, performance, maintenance, support, and disposal as appropriate
Analyze and quantify functionality required by end users, allocate them to functions and sub functions
Analyze requirements (stated, implicit and derived) to ensure that they are complete, feasible, realizable, and verifiable

## Slide 140: Important Points / New Aspects..
Identify technical performance measures that will be tracked during the development effort
Perform a risk assessment on the requirements and functional architecture

## Slide 141: Expected work products
Discussion

## Slide 142: Technical Solution
The purpose of Technical Solution is to design, develop, and implement solutions to requirements. Solutions, designs, and implementations encompass products, product components, and product-related life-cycle processes either singly or in combinations as appropriate

## Slide 143: Technical Solution
SG 1 | Select Product-Component Solutions
SP 1.1 SP 1.2 SP 1.3 | Develop Detailed Alternative Solutions and Selection Criteria Evolve Operational Concepts and Scenarios Select Product-Component Solutions
SG 2 | Develop the Design
SP 2.1 SP 2.2 SP 2.3 SP 2.4 | Design the Product or Product Component Establish a Technical Data Package Design Interfaces Using Criteria Perform Make, Buy, or Reuse Analyses

## Slide 144: Technical Solution
SG 3 | Implement the Product Design
SP 3.1 SP 3.2 | Implement the Design Develop Product Support Documentation

## Slide 145: Important Points / New Aspects..
Identify technologies currently in use and new product technologies for competitive advantage
Generate alternative solutions and obtain a complete requirements allocation for each alternative
Refine the operational concepts and scenarios
Select the best set of alternative solutions that satisfy the established selection criteria
Identify the product-component solutions that will be reused or acquired

## Slide 146: Important Points / New Aspects..
Establish and maintain criteria against which the design can be evaluated
Ensure that the design adheres to applicable design standards and criteria
Document the design in the technical data package
Document the rationale for key (i.e., significant effect on cost, schedule, or technical performance) decisions made or defined
Define interface using defined criteria
Develop criteria for the reuse of product-component designs / acquiring COTS components
Conduct peer reviews of the installation, operation, and maintenance documentation

## Slide 148: Product Integration
The purpose of Product Integration is to assemble the product from the product components, ensure that the product, as integrated, functions properly, and deliver the product

## Slide 149: Product Integration
SG 1 | Prepare for Product Integration
SP 1.1 SP 1.2 SP 1.3 | Determine Integration Sequence Establish the Product Integration Environment Establish Product Integration Procedures and Criteria
SG 2 | Ensure Interface Compatibility
SP 2.1 SP 2.2 | Review Interface Descriptions for Completeness Manage Interfaces

## Slide 150: Product Integration
SG 3 | Assemble Product Components and Deliver the Product
SP 3.1 SP 3.2 SP 3.3 SP 3.4 | Confirm Readiness of Product Components for Integration Assemble Product Components Evaluate Assembled Product Components Package and Deliver the Product or Product Component

## Slide 151: Important Points / New Aspects..
Identification of product components based on established standards
Identify the product integration verifications to be performed using the definition of the interfaces
Select the best integration sequence (Build)
Develop an integration environment if a suitable environment cannot be acquired
Establish and maintain criteria for validation and delivery of the integrated product
Review interface data for completeness and ensure complete coverage of all interfaces

## Slide 152: Important Points / New Aspects..
Maintain a repository for interface data accessible to project participants
Review the requirements, design, product, verification results, and documentation to ensure that issues affecting the packaging and delivery of the product are identified and resolved
Prepare the operational site for installation of the product
Install the product at the operational site and confirm correct operation

## Slide 154: Verification
The purpose of Verification is to ensure that selected work products meet their specified requirements

## Slide 155: Verification
SG 1 | Prepare for Verification
SP 1.1 SP 1.2 SP 1.3 | Select Work Products for Verification Establish the Verification Environment Establish Verification Procedures and Criteria
SG 2 | Perform Peer Reviews
SP 2.1 SP 2.2 SP 2.3 | Prepare for Peer Reviews Conduct Peer Reviews Analyze Peer Review Data

## Slide 156: Verification
SG 3 | Verify Selected Work Products
SP 3.1 SP 3.2 | Perform Verification Analyze Verification Results and Identify Corrective Action

## Slide 157: Important Points / New Aspects..
Define the verification methods to be used for each selected work product
Identify verification resources that are available for reuse and modification
Generate the set of comprehensive, integrated verification procedures for work products and any commercial off-the-shelf products, as necessary
Determine what type of peer review will be conducted
Establish and maintain criteria for requiring another peer review
Document the “as-run” verification method and the deviations from the available methods and procedures discovered during its performance

## Slide 159: Validation
The purpose of Validation is to demonstrate that a product or product component fulfills its intended use when placed in its intended environment

## Slide 160: Validation
SG 1 | Prepare for Validation
SP 1.1 SP 1.2 SP 1.3 | Select Products for Validation Establish the Validation Environment Establish Validation Procedures and Criteria
SG 2 | Validate Product or Product Components
SP 2.1 SP 2.2 | Perform Validation Analyze Validation Results

## Slide 161: Important Points / New Aspects..
Identify the key principles, features, and phases for product or product-component validation throughout the life of the project
Determine which categories of user needs (operational, maintenance, training, or support) are to be validated
Identify validation environment requirements
Document the environment, operational scenario, procedures, inputs, outputs, and criteria for the validation of the selected product or product component

## Slide 163: Module 6 - Support Process Areas

## Slide 164: Prelude
Objective is to give an overview of Support processes
Caution : Slides are Verbose and no animation used through out the presentation
Focus is on discussion

## Slide 165: Scope
Basic set of Support Processes
Measurement and Analysis (L2)
Process and Product Quality Assurance (L2)
Configuration Management (L2)
Advanced set of Support Processes
Decision Analysis and Resolution (L3)
Organizational Environment for integration (L3) – will be covered in next module.
Causal Analysis and Resolution(L5)

## Slide 166: Measurement and Analysis
Purpose
The purpose of Measurement and Analysis is to develop and sustain a measurement capability that is used to support management information needs

## Slide 167: Measurement and Analysis
SG 1 | Align Measurement and Analysis activities
SP 1.1 SP 1.2 SP 1.3 SP 1.4 | Establish Measurement objectives Specify Measures Specify Data collection and storage procedures Specify Analysis procedures
SG 2 | Provide Measurement Results
SP 2.1 SP 2.2 SP 2.3 SP 2.4 | Collect Measurement Data Analyze Measurement Data Store Data and Results Communicate Results

## Slide 168: Important Points / New Aspects..
Document information needs and objectives
Prioritize information needs and objectives
Maintain traceability of the measurement objectives to the identified information needs
Specify operational definitions
Support automatic collection of the data
Review and update the proposed content and format of the specified analysis and reports
Specify criteria for evaluating the utility of the analysis results and measurement program
Perform data integrity checks as close to the source of data as possible

## Slide 169: Discussion
What the barriers in implementing measurement programs ?
Probable work products

## Slide 170
Purpose
The purpose of Process and Product Quality Assurance is to provide staff and management with objective insight into processes and associated work products

## Slide 171: Process and Product Quality Assurance
SG 1 | Objectively Evaluate Processes and Work products
SP 1.1 SP 1.2 | Objectively evaluate processes Objectively evaluate work products and services
SG 2 | Provide objective insight
SP 2.1 SP 2.2 | Communicate and ensure resolution of non compliance issues Establish Records

## Slide 172: Important Points / New Aspects..
Promote an environment (created as part of project management) that encourages employee participation in identifying and reporting quality issues
Establish and maintain and use clearly stated criteria for the evaluation

## Slide 173: Discussion
Challenges in performing an objective quality assurance process
Can quality be achieved without quality assurance
Probable work products

## Slide 174: Configuration Management
Purpose
The purpose of Configuration Management is to establish and maintain the integrity of work products using configuration identification, configuration control, configuration status accounting, and configuration audits

## Slide 175: Configuration Management
SG 1 | Establish Baselines
SP 1.1 SP 1.2 SP 1.3 | Identify configuration items Establish a configuration Management system Create or Release baselines
SG 2 | Track and control changes
SP 2.1 SP 2.2 | Track change requests Control configuration items
SG 3 | Establish integrity
SP 3.1 SP 3.2 | Establish configuration management records Perform configuration audits

## Slide 176: Important Points / New Aspects..
Establish a mechanism to manage multiple control levels of configuration management
Obtain authorization from the configuration control board before creating or releasing baselines
Check in and check out configuration items from the configuration management system for incorporation of changes in a manner that maintains the correctness and integrity of the configuration items
Describe the difference between successive baselines
Revise the status and history of each configuration item

## Slide 177: Discussion
Challenges in implementing Configuration Management systems and maintaining history

## Slide 178: Decision Analysis and Resolution
Purpose
The purpose of Decision Analysis and Resolution is to analyze possible decisions using a formal evaluation process that evaluates identified alternatives against established criteria
We will look at this PA in more detail

## Slide 179: Decision Analysis and Resolution
SG 1 | Evaluate alternatives
SP 1.1 SP 1.2 SP 1.3 SP 1.4 SP 1.5 SP 1.6 | Establish Guidelines for Decision Analysis Establish evaluation criteria Identify alternative solutions Select evaluation methods Evaluate alternatives Select solutions

## Slide 180: SP1.1 Establish Guidelines for Decision Analysis
Establish guidelines
Incorporate the use of the guidelines into the defined process where appropriate

## Slide 181: SP1.2 Establish evaluation criteria
Define the criteria for evaluating alternative solutions
Define the range and scale for ranking the evaluation criteria
Rank the criteria
Assess the criteria and their relative importance
Evolve the evaluation criteria to improve their validity
Document the rationale for the selection and rejection of evaluation criteria

## Slide 182: SP1.3 Identify alternative solutions
Perform a literature search
Identify alternatives for consideration in addition to those that may be provided with the issue
Document the proposed altrnatives

## Slide 183: SP1.4 Select evaluation methods
Select the methods based on the purpose for analyzing a decision and on the availability of the information used to support the method
Select evaluation method based on their ability to focus on the issues at hand without being overly influenced by side issues
Determine the measures needed to support the evaluation method

## Slide 184: SP1.5 Evaluate Alternatives
Evaluate the proposed alternative solutions using the established evaluation criteria and selected methods
Evaluate the assumptions related to the evaluation criteria and the evidence that supports the assumptions
Evaluate whether the uncertainty in the values for alternative solutions effects the evaluation and address as appropriate
Perform simulations, modeling, prototypes, and pilots as necessary
Consider new alternative solutions, if the proposed alternative do not test well
Document results of evaluation

## Slide 185: SP1.6 Select solutions
Assess the risks associated with implementing the recommended solution
Document the results and rationale for the recommended solution

## Slide 186: Discussion
What activities in your organization require formal decision making process ?
Is there any formal mechanism currently in place ?

## Slide 187: Causal Analysis and Resolution
Purpose
The purpose of Causal Analysis and Resolution is to identify causes of defects and other problems and take action to prevent them from occurring in future.

## Slide 188: Causal Analysis and Resolution
SG 1 | Determine Causes of Defects
SP 1.1 SP 1.2 | Select defect data for analysis Analyze causes
SG 2 | Address Causes of Defects
SP 2.1 SP 2.2 SP 2.3 | Implement the action proposals Evaluate effect of changes Record data

## Slide 189: What’s new
Determine which defects and other problems will be analyzed and select methods
Conduct causal analysis with people who are responsible for performing the task
Measure the change in the performance of the project’s defined process as appropriate
Measure the capability of the project’s defined process as appropriate

## Slide 190: Discussion
What could be an effective method of performing causal analysis ?
When and who should do it ?
Probable work products

## Slide 191: Module 7 - Summary and Discussions

## Slide 192: We hope you have now …
An overview of the CMMI Product Suite
The ability to locate and begin to apply relevant information in the model document to your organization
Awareness of the components of CMMI models and how it can be applied
Awareness about model structure, and important model relationships
Awareness of behavioral characteristics associated with each maturity level

## Slide 193: Revisit Course Expectations
Discussion: Were your expectations met?

## Slide 194
Hari P Thapliyal,
PMP, PMI-ACP, MCITP, Princ2 Practitioner, CSM, MBA, MCA, CIC, PGDFM
PMO Architect & Project Management Evangelist
Profile: http://in.linkedin.com/in/harithapliyal
For content related queries please contact me via
hari.prasad@vedavit-ps.com
This document is proprietary and confidential. It remains the property of Vedavit Project Solutions at all times. No part of this document may be used, reproduced, or transmitted in any form or by any means electronic, including photocopying and recording, for any purpose without express consent of Vedavit Project Solutions.